## 11_7
Software Design Plan Of Work |  |  |  | Week of 11/7
SUNDAY
MONDAY
TUESDAY | Read and Understand rules and requlations
WEDNESDAY | Have a problem to solve with the program | Create a working list of components needed to finish the program | Create a plan of work for the program
THURSDAY | Begin research and research and design work on web parser
FRIDAY
SATURDAY | Finish research and design work on web parser | Begin development of web parser

## 11_21
Software Design Plan Of Work |  |  | Week of 11/21
SUNDAY
MONDAY
TUESDAY
WEDNESDAY
THURSDAY | Finish Work on Web Parser | Begin research and design work on user interface
FRIDAY
SATURDAY

## 11_28
Software Design Plan Of Work |  |  | Week of 11/28
SUNDAY
MONDAY
TUESDAY
WEDNESDAY
THURSDAY | Finish user interface research and design work | Begin user interface development
FRIDAY
SATURDAY

## 12_5
Software Design Plan Of Work |  |  | Week of 12/5
SUNDAY
MONDAY
TUESDAY
WEDNESDAY
THURSDAY | Finish development of user interface | Begin research and design for summary gereratior
FRIDAY
SATURDAY

## 12_12
Software Design Plan Of Work |  |  |  | Week of 12/12
SUNDAY
MONDAY
TUESDAY
WEDNESDAY
THURSDAY | Finish research and design for summary generatior | Begin development on summary generatior | Begin Binder finalization
FRIDAY
SATURDAY

## 12_19
Software Design Plan Of Work |  |  |  | Week of 12/19
SUNDAY
MONDAY | Eliminate all bugs
TUESDAY
WEDNESDAY
THURSDAY | Eliminate all bugs due | Finish development on summary generatior | Finish binder finalization | Project Complete
FRIDAY
SATURDAY